## Sheet1
ID | User Stories | Initial hours | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Day 0 | Total Hours
9 | As a registered customer, I want to log in to my AGME account, so that I can gain access to my personal dashboard. | 20 | 0 | 0 | 5 | 0 | 10 | 0 | 0 | 5 | 0 | 0 | 20
5 | As a worker, I want to access my profile, so that I can see my assigned working hours/ days and services. | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 15
11 | As an unregistered customer, I want to be able to sign up an account, so that I can login and use the online booking service. | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 10
13 | As a guest user, I want to sign up for an AGME account, so that I can have my personal dashboard. | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10
50 | As an admin, I want to be able to log in to my account, so that I can view my business details. | 20 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 15
| Total Hours Remaining | 100 | 90 | 85 | 80 | 75 | 65 | 65 | 60 | 45 | 40 | 30 | 70
| Expected Hours Remaining | 100 | 90 | 80 | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0
Initial Hours | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Day 0
100 | 90 | 85 | 80 | 75 | 65 | 65 | 60 | 45 | 40 | 30
100 | 90 | 80 | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0